## Record of Change
Security Classification: Confidential
Document History
Document Location
File Name |  | Location
Assignment2_KimAnh_MiddleTerm.xltx |  | Process Asset Library
Document Version History
Version | Effective Date | Author | Details | Reviewer | Approvers
For previous versions, please refer PIP_Master List

## Instruction
Security Classification: Confidential
| Instruction |  |  |  |  | <<Client Logo>>
| <<Client Name>> |  |  | <<Project Name>>
1. Purpose
Test Case is a set of test inputs, execution conditions, and expected results developed for particular objective, such as to exercise a particular program path or to verify compliance with a specific requirement.
The purpose of the Test Case is to identify and communicate the conditions, which will be implemented and are necessary to verify successful and acceptable implementation of the project.
QC will perform tests and give the result in the test case.
2. How to Use
Test Case List | List all test cases sheet in the file. Each function has a sheet. Generally, each sheet is test case of a UC
Other sheets | There is no specific template for using the test case in the scrum process. It depends on the project, the QC will define how to write test case.
However, how to write test case must be defined in the test strategy/test plan.
There are two samples: "user story 1" and "user story 2"
3. Test Result
Passed | The actual result is met the expected result
Failed | The actual result is NOT met the expected result
Not Run | By some reasons, the cases can't be run: The system has bug and the case can't be run.
4. Bug is not met any case in the test cases
During testing, the QC is able to find a bug which is not met any case in the test case. In this situation, QC need to add the case into the related function as an ad-hoc case.
The step: is the step to reproduce bug.
The expected result: mention the actual and expected result of the bug
Test case #18: Ad-hoc testing
|  | Detail the task as the bug description | Actual result: - - Expectation: - -
5. Test Report
The test report is using for all sprints of the project.

## Cover
Cover
TEST CASE LIST
No. | Sprint # | Function Name | Sheet Name | Description | Pre-Condition
1 |  | Common checklist | Common checklist
2 | Sprint 1 | User Story 1 | User Story 1
3 | Sprint 1 | User Story 2 | User Story 2
4 | Sprint 2
5 | Sprint 2
6 | Sprint 3
7 | Sprint 3

## Common checklist
Common Checklist
No. | Checking item | Expectation | Result
1
2
3
4
5
6
7
8
9
* Note:
[ x ] has verified
Note on D5: Nhan Nguyen Hoang: Yes/No/NA NA: there is no page to check.

## User Story 1
Common Checklist
User Story 1 | Search Product Function | [7 empty] | Pass
Description | [8 empty] | Fail - DE
Pre-condition
Tested by | Kim Anh
Test Date
Test Result | Internal Build 03112011 | Internal build 14112011 | External build 16112011
Total | 0 | 0 | 0
Passed | 0 | 0 | 0
Failed | 0 | 0 | 0
Not Run | 0 | 0 | 0
NA | 0 | 0 | 0
Passed in previous build | 0 | 0 | 0
Test Result
ID | Test Case Description | Step | Expected Output | Test Data | Internal Build 03112011 | Internal build 14112011 | External build 16112011 | Note
1. Entering in search bar
1 | Verify initial data in search bar is a placeholder
2 | Verify search working by entering in search bar only 1 keyword product
3 | Verify search working by entering in search bar 2 keyword product
4 | Verify user can copy and paste into search box
5 | Verify search working by entering only 1 word of product / category / brand / supplier name | 8 testcase : 1 phan product name va full product name …. Cho 3 cai khac
6 | Verify search working by entering multiple words of product / category / brand / supplier name | search 2 key
7 | Verify user can hit enter on keyboard to submit searching
8 | Verify user can click on button find to submit searching
9 | Verify when user enter HTML, JS or SQL injection into search box
10 | Verify inputted data is trim when input spaces at front and end of text
11 | Verify when user finding with empty search box
12 | Verify when entering only a space/spaces in searchbox
13 | Verify search working by entering valid uppercase input
14 | Verify entering characters between multiple words of product/category/brand/supplier name
15 | Verify when text in search box do not match any data , page will display message "Search No Result"
2. Search suggestion
16 | Verify no suggestion is displayed when user do not enter anything | search suggestion can be click | chua nhap gi , nhap 1 tu khoa, nhap 1 key word, xoa bot di se thay doi, 5 case
17 | Verify search suggestion displayed when user input a character
18 | Verify search suggestion displayed when user input multiple characters
3. Search history
19 | Verify no search history is displayed when user did not search anything before |  | 0 , 1 and any value > 1 - ko chot 1 con so cu the
20 | Verify when user click on search box, search history is displayed |  | 0 va lon hon 0
21 | Verify search history result is match with the real search user entered before
22 | Verify user can click on text CLEAR to clear all search history
4. Navigation
23 | Verify there is no navigation when search result has less than 10 products
24 | Verify there is no navigation when search result has exactly 10 products | <10, 10 ,11, >11, button,
25 | Verify number navigated pages when search results has more than 10 products
26 | Verify number products per navigated page when search results has more than 10 products
27 | Verify products in next page must be products continue after 10 products from previous page
28 | Verify user can click button >, < in navigation part
29 | Verify status button > in navigation part is disable when current page is the last
30 | Verify status button < in navigation part is disable when current page is the first
31 | Verify user can click at number page in navigation part to change page
5. Sorting
32 | Verify user can click on selection sorted part to select sorted by price low to high, high to low
33 | Verify selection sorted by price low to high when search result has 1 product | 1 high to low, low to high, default
34 | Verify selection sorted by price high to low when search result has 1 product
35 | Verify sorting by price low to high when search result has 10 products
36 | Verify sorting by price high to low when search result has 10 products
37 | Verify sorting by price low to high applied for all navigation pages when search result has more than 10 products
38 | Verify sorting by price high to low applied for all navigation pages when search result has more than 10 products
39 | Verify user can click on product to move to detail link of that product
Note on F17: Pass Fail Untested N/A
Note on G17: Pass Fail Untested N/A
Note on H17: Pass Fail Untested N/A
Note on F42: Nguyen Dao Thi Binh: Bug ID: 13050
Note on F44: Nguyen Dao Thi Binh: Bug ID: 13050

## Test report
Security Classification: Confidential
|  | End Sprint Test report |  |  |  |  | <<<<Client Logo>>>>
|  | <<<<Client Name>>>> |  |  | <<<<Project Name>>>>
1. Scope of sprint
<<List all the User story which be tested in this sprint, Epic ID and Epic Name field can be removed / modified if needed>>
No. | US ID | US Summary | Epic ID | Epic Name | Environment | Dev Status | QC status | Notes
| <<US ID>> | <<US Summary>> | <<Epic ID>> | <<Epic Name>> | <<Environment>> | <<Dev status>> | <<QC status>>
1 | User Story 1 | US summary | PRT-1 | Epic name 1 | PROD | Done | Done
2 | User Story 2 | US summary 2 | PRT-4 | Epic name 2 | PROD | Done | N/A | Out of scope of testing
2. Test case status in summary
<<List all the test case which be tested for each User story in this sprint>>
No. | US ID | Passed | Failed | N/A | Not Run | Passed in previous builds
| <<US ID>> | <<number of passed>> | <<number of fail cases>> | <<number of n/a>> | <<number of not run>> | <<number of passed in previous build>>
1 | User Story 1 | 0 | 0 | 0 | 0 | 0
2 | Total | 0 | 0 | 0 | 0 | 0
|  | Test coverage | #DIV/0!
3. Bug status
<<The summary information for bugs found in this sprint>>
3.1 Bug summary
No. | Total | New | Resolved | Reopened | Verified / Closed | Note
1 | Critical | #REF! | #REF! | #REF! | #REF!
2 | Major | #REF! | #REF! | #REF! | #REF!
3 | Normal | #REF! | #REF! | #REF! | #REF!
4 | Minor | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | 0 | 0 | #REF!
3.2 Open Bug
No. | Bug ID | Bug Summary | Priority | Environment | Notes
| <<Bug ID>> | <<Bug summary>> | <<Priority>> | <<Environment>>
1 | US3-1 | Bug summary 1 | Minor | PROD
2 | US1-1 | Bug summary | Minor | PROD
4. Risk & Issue
<<Describe the risk, issue, recommendation from QC point of view for this project>>
No. | Description | Mitigation Strategy |  | Contingency (Risk is realized) |  |  | Created Date
1 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
2 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
3 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
5. QC evaluation
<<Describe the QC evaluation for each sprint based on the DoD of project>>
No. | DoD Criteria | Number of Defects |  |  |  | Test coverage | DoD Criteria | QC End Sprint report status
|  | Critical | Major | Normal | Minor
|  | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
1 | <<Sprint number>> | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
2 | Sprint 1 | 0 | 0 | 0 | #REF! | #DIV/0! | PASS | PASS