## Record of Change
Security Classification: Confidential
Document History
Document Location
File Name |  | Location
Assignment2_KimAnh_MiddleTerm.xltx |  | Process Asset Library
Document Version History
Version | Effective Date | Author | Details | Reviewer | Approvers
For previous versions, please refer PIP_Master List

## Instruction
Security Classification: Confidential
| Instruction |  |  |  |  | <<Client Logo>>
| <<Client Name>> |  |  | <<Project Name>>
1. Purpose
Test Case is a set of test inputs, execution conditions, and expected results developed for particular objective, such as to exercise a particular program path or to verify compliance with a specific requirement.
The purpose of the Test Case is to identify and communicate the conditions, which will be implemented and are necessary to verify successful and acceptable implementation of the project.
QC will perform tests and give the result in the test case.
2. How to Use
Test Case List | List all test cases sheet in the file. Each function has a sheet. Generally, each sheet is test case of a UC
Other sheets | There is no specific template for using the test case in the scrum process. It depends on the project, the QC will define how to write test case.
However, how to write test case must be defined in the test strategy/test plan.
There are two samples: "user story 1" and "user story 2"
3. Test Result
Passed | The actual result is met the expected result
Failed | The actual result is NOT met the expected result
Not Run | By some reasons, the cases can't be run: The system has bug and the case can't be run.
4. Bug is not met any case in the test cases
During testing, the QC is able to find a bug which is not met any case in the test case. In this situation, QC need to add the case into the related function as an ad-hoc case.
The step: is the step to reproduce bug.
The expected result: mention the actual and expected result of the bug
Test case #18: Ad-hoc testing
|  | Detail the task as the bug description | Actual result: - - Expectation: - -
5. Test Report
The test report is using for all sprints of the project.

## Cover
Cover
TEST CASE LIST
No. | Sprint # | Function Name | Sheet Name | Description | Pre-Condition
1 |  | Common checklist | Common checklist
2 | Sprint 1 | User Story 1 | User Story 1
3 | Sprint 1 | User Story 2 | User Story 2
4 | Sprint 2
5 | Sprint 2
6 | Sprint 3
7 | Sprint 3

## Common checklist
Common Checklist
No. | Checking item | Expectation | Result
1
2
3
4
5
6
7
8
9
* Note:
[ x ] has verified
Note on D5: Nhan Nguyen Hoang: Yes/No/NA NA: there is no page to check.

## User Story 1
Common Checklist
User Story 1 | Search Product Function | [7 empty] | Pass
Description | [8 empty] | Fail - DE
Pre-condition | Go to website which has search product function
Tested by | Kim Anh
Test Date
Test Result | Internal Build 03112011 | Internal build 14112011 | External build 16112011
Total | 0 | 0 | 0
Passed | 0 | 0 | 0
Failed | 0 | 0 | 0
Not Run | 0 | 0 | 0
NA | 0 | 0 | 0
Passed in previous build | 0 | 0 | 0
Test Result
ID | Test Case Description | Step | Expected Output | Test Data | Internal Build 03112011 | Internal build 14112011 | External build 16112011 | Note
1. Entering in search bar
1 | Verify initial data in search bar is a placeholder | 1. Observe search bar | There is a placeholder in bar
2 | Verify user can click on button find to submit searching | 1. Click on search bar 2. Enter a product 3. Click on search button | Search works and display related product list | scope test la gi. Hinh dung tap dau vao dau ra de co cac case ra sao. Confirm requirement
3 | Verify when user enter HTML, JS or SQL injection into search box | 1. Click on search bar 2. Enter <input> 3. Click on search button | Search works and does not take character "<" and ">" to find
4 | Verify search working when enter a part of product name | 1. Click on search bar 2. Enter "tu" 3. Click on search button | Page displays result list contains "tu" in others part or product name part
5 | Verify search working when enter full of product name | 1. Click on search bar 2. Enter "tu lanh" 3. Click on search button | Page displays result list contains "tu lanh" in others part or product name part
6 | Verify search working when enter a part of category name | 1. Click on search bar 2. Enter "quay" 3. Click on search button | Page displays result list contains "quay" in others part or category name part
7 | Verify search working when enter full of category name | 1. Click on search bar 2. Enter "heo quay" 3. Click on search button | Page displays result list contains "heo quay" in others part or category name part
8 | Verify search working when enter a part of brand name | 1. Click on search bar 2. Enter "adi" 3. Click on search button | Page displays result list contains "adi" in others part or brand name part
9 | Verify search working when enter full of brand name | 1. Click on search bar 2. Enter "adidas" 3. Click on search button | Page displays result list contains "adidas " in others part or brand name part
10 | Verify search working when enter a part of supplier name | 1. Click on search bar 2. Enter "Wa" 3. Click on search button | Page displays result list contains "Wa" in others part or supplier name part
11 | Verify search working when enter full of supplier name | 1. Click on search bar 2. Enter "Wakabook" 3. Click on search button | Page displays result list contains "Wakabook" in others part or supplier name part
12 | Verify when user finding with empty search box | 1. Click on search bar 2. Let it empty 3. Click on search button | Search does nothing
13 | Verify user can hit enter on keyboard to submit searching | 1. Click on search bar 2. Enter a product 3. Press enter on keyboard | Search works and display products contains keyword
14 | Verify user can copy and paste into search box | 1. Click on search bar 2. Enter a text 3. Copy the text above 4. Delete content in search bar 5. Paste the copied into field again 6. Click on search button | 1. There is no error displayed 2. Search works and display correct result
15 | Verify when entering only a space/spaces in searchbox | 1. Click on search bar 2. Enter many spaces 3. Click on search button | Search does nothing
16 | Verify search working by entering valid uppercase input | 1. Click on search bar 2. Enter a product in UpperCase 3. Click on search button | Search works and display products contains keyword
17 | Verify entering characters between multiple words of product/category/brand/supplier name | 1. Click on search bar 2. Enter "tu lanh & may giat " 3. Click on search button | Search works and display products contains any one of 2 keywords
18 | Verify when text in search box do not match any data , page will display message "Search No Result" | 1. Click on search bar 2. Enter "abhsgeuriflg" 3. Click on search button | Page will display a message "Search No Result"
2. Search suggestion
19 | Verify no suggestion is displayed when user do not enter anything | 1. Click on search bar 2. Observe search bar | No suggestion is displayed
20 | Verify search suggestion displayed when user input a character | 1. Click on search bar 2. Enter "tu" 3. Observe search suggestion | Search suggestion is displayed and suggestion contains keyword
21 | Verify search suggestion displayed when user input multiple characters | 1. Click on search bar 2. Enter "tu lanh" 3. Observe search suggestion | Search suggestion is displayed and suggestion contains whole keyword
22 | Verify search suggestion will change when user delete a character in search box | 1. Click on search bar 2. Enter "tu lanh" 3. Observe search suggestion 4. Delete "lanh" 5. Observe search suggestion | 2. Suggestion contains keyword 5. Suggestion will change to contains only "tu"
3. Search history
23 | Verify no search history is displayed when user did not search anything before | 1. Click on search bar when search box is not searched before 2. Observe search history | Nothing is displayed on search bar
24 | Verify displaying history when user had searched only 1 text before | 1. Click on search bar 2. Enter "tu lanh" 3. Click on search button 4. Click on search bar 5. Observe search history | Search history shows only 1 results and match with the text user searched before
25 | Verify search history result when user had search more than 1 text before | 1. Click on search bar 2. Search multiple times 3. Click on search bar 4. Observe search history | Search history shows number results and match with the number searching user searched before
26 | Verify user can click on text CLEAR to clear all search history | 1. Click on search bar 2. Click on CLEAR 3. Observe search history | No search history is displayed
4. Navigation
27 | Verify there is no navigation when search result has less than 10 products | 1. Click on search bar 2. Search a product less than 10 results 3. Observe part under last products | There is no navigation part
28 | Verify there is no navigation when search result has exactly 10 products | 1. Click on search bar 2. Search a product has 10 results 3. Observe part under last products | There is no navigation part
29 | Verify number navigated pages when search results has 11 products | 1. Click on search bar 2. Search a product has 11 results 3. Observe navigation part | There is 2 page in navigation part
30 | Verify number products per navigated page when search results has more than 11 products | 1. Click on search bar 2. Search a product has more than 11 results 3. Click on page 1 of navigation part 4. Count number of products in page 1 | Page 1 and other page should have exactly 10 products in each page
31 | Verify user can click at number page in navigation part to change page | 1. Click on search bar 2. Search a product has more than 10 results 3. Click on a number page of navigation part | Number page can be clicked and redirect to number page contains 10 products in list
32 | Verify status button > in navigation part is disable when current page is the last | 1. Click on search bar 2. Search a product has more than 10 results 3. Click on last page of navigation part 4. Click on button ">" | Button can not be clicked
33 | Verify status button < in navigation part is disable when current page is the first | 1. Click on search bar 2. Search a product has more than 10 results 3. Click on first page of navigation part 4. Click on button "<" | Button can not be clicked
34 | Verify user can click on product to move to detail link of that product | 1. Click on search bar 2. Search a product has more than 10 results 3. Click on a number page of navigation part 4. Click on a product | Redirect to page show details and sell that product
5. Sorting (default is low to high)
35 | Verify selection sorted by price high to low when search result has 1 product | 1. Click on search bar 2. Search a product has 1 result 3. Observe page 4. Click on sort part to select low to high sorting 5. Observe page | Page is displayed 1 product
36 | Verify sorting by price high to low when search result has 10 products | 1. Click on search bar 2. Search a product has 10 result 3. Observe products list 4. Click on sort part to select low to high sorting 5. Observe products list | 3. Page will show results list from low to high price 5. Page will show results list from high to low price
37 | Verify sorting by price high to low applied for all navigation pages when search result has more than 10 products | 1. Click on search bar 2. Search a product has more than 10 result 3. Observe products list 4. Click on page after current page in navigation part 5. Observe products list 6. Click on sort part to select low to high sorting 7. Observe products list 8. Click on page after current page in navigation part 9. Observe products list | 5. Default low to high sorting is correct for all navigation page 9. High to low sorting is correct for all navigation page
Note on F17: Pass Fail Untested N/A
Note on G17: Pass Fail Untested N/A
Note on H17: Pass Fail Untested N/A
Note on F46: Nguyen Dao Thi Binh: Bug ID: 13050
Note on F48: Nguyen Dao Thi Binh: Bug ID: 13050

## Test report
Security Classification: Confidential
|  | End Sprint Test report |  |  |  |  | <<<<Client Logo>>>>
|  | <<<<Client Name>>>> |  |  | <<<<Project Name>>>>
1. Scope of sprint
<<List all the User story which be tested in this sprint, Epic ID and Epic Name field can be removed / modified if needed>>
No. | US ID | US Summary | Epic ID | Epic Name | Environment | Dev Status | QC status | Notes
| <<US ID>> | <<US Summary>> | <<Epic ID>> | <<Epic Name>> | <<Environment>> | <<Dev status>> | <<QC status>>
1 | User Story 1 | US summary | PRT-1 | Epic name 1 | PROD | Done | Done
2 | User Story 2 | US summary 2 | PRT-4 | Epic name 2 | PROD | Done | N/A | Out of scope of testing
2. Test case status in summary
<<List all the test case which be tested for each User story in this sprint>>
No. | US ID | Passed | Failed | N/A | Not Run | Passed in previous builds
| <<US ID>> | <<number of passed>> | <<number of fail cases>> | <<number of n/a>> | <<number of not run>> | <<number of passed in previous build>>
1 | User Story 1 | 0 | 0 | 0 | 0 | 0
2 | Total | 0 | 0 | 0 | 0 | 0
|  | Test coverage | #DIV/0!
3. Bug status
<<The summary information for bugs found in this sprint>>
3.1 Bug summary
No. | Total | New | Resolved | Reopened | Verified / Closed | Note
1 | Critical | #REF! | #REF! | #REF! | #REF!
2 | Major | #REF! | #REF! | #REF! | #REF!
3 | Normal | #REF! | #REF! | #REF! | #REF!
4 | Minor | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | 0 | 0 | #REF!
3.2 Open Bug
No. | Bug ID | Bug Summary | Priority | Environment | Notes
| <<Bug ID>> | <<Bug summary>> | <<Priority>> | <<Environment>>
1 | US3-1 | Bug summary 1 | Minor | PROD
2 | US1-1 | Bug summary | Minor | PROD
4. Risk & Issue
<<Describe the risk, issue, recommendation from QC point of view for this project>>
No. | Description | Mitigation Strategy |  | Contingency (Risk is realized) |  |  | Created Date
1 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
2 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
3 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
5. QC evaluation
<<Describe the QC evaluation for each sprint based on the DoD of project>>
No. | DoD Criteria | Number of Defects |  |  |  | Test coverage | DoD Criteria | QC End Sprint report status
|  | Critical | Major | Normal | Minor
|  | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
1 | <<Sprint number>> | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
2 | Sprint 1 | 0 | 0 | 0 | #REF! | #DIV/0! | PASS | PASS