## Record of Change
Security Classification: Confidential
Document History
Document Location
File Name |  | Location
Assignment2_KimAnh_MiddleTerm.xltx |  | Process Asset Library
Document Version History
Version | Effective Date | Author | Details | Reviewer | Approvers
For previous versions, please refer PIP_Master List

## Instruction
Security Classification: Confidential
| Instruction |  |  |  |  | <<Client Logo>>
| <<Client Name>> |  |  | <<Project Name>>
1. Purpose
Test Case is a set of test inputs, execution conditions, and expected results developed for particular objective, such as to exercise a particular program path or to verify compliance with a specific requirement.
The purpose of the Test Case is to identify and communicate the conditions, which will be implemented and are necessary to verify successful and acceptable implementation of the project.
QC will perform tests and give the result in the test case.
2. How to Use
Test Case List | List all test cases sheet in the file. Each function has a sheet. Generally, each sheet is test case of a UC
Other sheets | There is no specific template for using the test case in the scrum process. It depends on the project, the QC will define how to write test case.
However, how to write test case must be defined in the test strategy/test plan.
There are two samples: "user story 1" and "user story 2"
3. Test Result
Passed | The actual result is met the expected result
Failed | The actual result is NOT met the expected result
Not Run | By some reasons, the cases can't be run: The system has bug and the case can't be run.
4. Bug is not met any case in the test cases
During testing, the QC is able to find a bug which is not met any case in the test case. In this situation, QC need to add the case into the related function as an ad-hoc case.
The step: is the step to reproduce bug.
The expected result: mention the actual and expected result of the bug
Test case #18: Ad-hoc testing
|  | Detail the task as the bug description | Actual result: - - Expectation: - -
5. Test Report
The test report is using for all sprints of the project.

## Cover
Cover
TEST CASE LIST
No. | Sprint # | Function Name | Sheet Name | Description | Pre-Condition
1 |  | Common checklist | Common checklist
2 | Sprint 1 | User Story 1 | User Story 1
3 | Sprint 1 | User Story 2 | User Story 2
4 | Sprint 2
5 | Sprint 2
6 | Sprint 3
7 | Sprint 3

## Common checklist
Common Checklist
No. | Checking item | Expectation | Result
1
2
3
4
5
6
7
8
9
* Note:
[ x ] has verified
Note on D5: Nhan Nguyen Hoang: Yes/No/NA NA: there is no page to check.

## User Story 1
Common Checklist
User Story 1 | Add new Address function | [7 empty] | Pass
Description | [8 empty] | Fail - DE
Pre-condition | 1. Access to Lazada page 2.Open add new address page
Tested by | Kim Anh
Test Date
Test Result | Internal Build 03112011 | Internal build 14112011 | External build 16112011
Total | 0 | 0 | 0
Passed | 0 | 0 | 0
Failed | 0 | 0 | 0
Not Run | 0 | 0 | 0
NA | 0 | 0 | 0
Passed in previous build | 0 | 0 | 0
Test Result
ID | Test Case Description | Step | Expected Output | Test Data | Internal Build 03112011 | Internal build 14112011 | External build 16112011 | Note
1. Validation field
1.1 Fullname
1 | Verify initial data in fullname field is blank
2 | Verify when enter only tab/spaces in fullname field
3 | Verify required fullname field when not filling data
4 | Verify it automatically trim space from front and end of inputted text when submit
5 | Verify field let user copy & paste
6 | Verify user can click on button x to clear inputted data
7 | Verify error when total characters in fullname is less than 2
8 | Verify error when total characters in fullname is more than 50
9 | Verify error when total characters in fullname is minlength 2
10 | Verify error when total characters in fullname is maxlength 50
11 | Verify when total characters in fullname field is between 6 and 50
12 | Verify when enter characters are not alphanumeric in fullname field
13 | Verify when enter characters are alphanumeric and valid length in fullname field
1.2 Phone number
14 | Verify initial data in phone number field is blank
15 | Verify required phone number field when not filling data
16 | Verify error when input alphabet and special characters in phone number field
17 | Verify input HTML, SQL injection in phone number field
28 | Verify user enters blank space between number
29 | Verify user can click on button x to clear inputted data
30 | Verify field let user copy & paste
31 | Verify total numeric characters input is 10 and valid
32 | Verify error when total numeric characters input is less than 10 and more than 0
33 | Verify error when total numeric characters input is more than 10
1.3 Address
34 | Verify initial data in Address field is blank
35 | Verify required Address field when not filling data
36 | Verify when enter only tab/spaces in fullname field
37 | Verify when enter characters are not alphanumeric in Address field
38 | Verify it automatically trim space from front and end of inputted text when submit
39 | Verify user can click on button x to clear inputted data
40 | Verify field let user copy & paste
41 | Verify error when total characters inputted is more than 350
42 | Verify error when total characters in Address field is less than 5
43 | Verify error when total characters in in Address field is minlength 5
44 | Verify error when total characters in in Address field is maxlength 350
45 | Verify when total characters in in Address field is between 5 and 350
46 | Verify when enter characters are alphanumeric and valid length in Address field
1.4 Province
47 | Verify initial data in Province field is blank
48 | Verify drop down values of field
49 | Verify error when user do not choose any value
50 | Verify when user choose a value from list
51 | Verify when user choose a value and then choose another value from list
52 | Verify displaying scroll bar when it has many data
1.5 District
53 | Verify initial data in District field is blank
54 | Verify drop down values of field depened on choosen Province in province field
55 | Verify no drop down value when user do not choose in Province field
56 | Verify error when user do not choose any value
57 | Verify when user choose a value from list
58 | Verify when user choose a value and then choose another value from list
59 | Verify displaying scroll bar when it has many data
1.6 Ward
60 | Verify initial data in Ward field is blank
61 | Verify displaying scroll bar when it has many data
62 | Verify drop down values of field depened on choosen District in district field
63 | Verify no drop down value when user do not choose in District field
64 | Verify error when user do not choose any value
65 | Verify when user choose a value from list
66 | Verify when user choose a value and then choose another value from list
1.7 Button
67 | Verify default value of effective delivery is Home / Office
68 | Verify label Office can be choosen
69 | Verify label Home can be choosen
2. Function
70 | Verify clicking on button CANCEL when do not fill in any field
71 | Verify clicking on button CANCEL when inputted fields have data
72 | Verify new address add successfully when all fields are valid with as Home
73 | Verify new address add successfully when all fields are valid with as Office
74 | Verify new address is displayed on the top of Address Book
75 | Verify error message is displayed when user loose focus on each fields with invalid input
76 | Verify user can click on button ADD NEW ADDRESS and redirect to add address page
77 | Verify value and informations in Address Book is match with what inputted in fields before
78 | Verify inputting data is similar to existed address
79 | Verfiy inputting multiples address with the same fullname and phone number
Note on F17: Pass Fail Untested N/A
Note on G17: Pass Fail Untested N/A
Note on H17: Pass Fail Untested N/A
Note on F48: Nguyen Dao Thi Binh: Bug ID: 13050
Note on F52: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F54: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F55: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F59: Nguyen Dao Thi Binh: Bug ID: 13057

## Test report
Security Classification: Confidential
|  | End Sprint Test report |  |  |  |  | <<<<Client Logo>>>>
|  | <<<<Client Name>>>> |  |  | <<<<Project Name>>>>
1. Scope of sprint
<<List all the User story which be tested in this sprint, Epic ID and Epic Name field can be removed / modified if needed>>
No. | US ID | US Summary | Epic ID | Epic Name | Environment | Dev Status | QC status | Notes
| <<US ID>> | <<US Summary>> | <<Epic ID>> | <<Epic Name>> | <<Environment>> | <<Dev status>> | <<QC status>>
1 | User Story 1 | US summary | PRT-1 | Epic name 1 | PROD | Done | Done
2 | User Story 2 | US summary 2 | PRT-4 | Epic name 2 | PROD | Done | N/A | Out of scope of testing
2. Test case status in summary
<<List all the test case which be tested for each User story in this sprint>>
No. | US ID | Passed | Failed | N/A | Not Run | Passed in previous builds
| <<US ID>> | <<number of passed>> | <<number of fail cases>> | <<number of n/a>> | <<number of not run>> | <<number of passed in previous build>>
1 | User Story 1 | 0 | 0 | 0 | 0 | 0
2 | Total | 0 | 0 | 0 | 0 | 0
|  | Test coverage | #DIV/0!
3. Bug status
<<The summary information for bugs found in this sprint>>
3.1 Bug summary
No. | Total | New | Resolved | Reopened | Verified / Closed | Note
1 | Critical | #REF! | #REF! | #REF! | #REF!
2 | Major | #REF! | #REF! | #REF! | #REF!
3 | Normal | #REF! | #REF! | #REF! | #REF!
4 | Minor | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | 0 | 0 | #REF!
3.2 Open Bug
No. | Bug ID | Bug Summary | Priority | Environment | Notes
| <<Bug ID>> | <<Bug summary>> | <<Priority>> | <<Environment>>
1 | US3-1 | Bug summary 1 | Minor | PROD
2 | US1-1 | Bug summary | Minor | PROD
4. Risk & Issue
<<Describe the risk, issue, recommendation from QC point of view for this project>>
No. | Description | Mitigation Strategy |  | Contingency (Risk is realized) |  |  | Created Date
1 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
2 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
3 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
5. QC evaluation
<<Describe the QC evaluation for each sprint based on the DoD of project>>
No. | DoD Criteria | Number of Defects |  |  |  | Test coverage | DoD Criteria | QC End Sprint report status
|  | Critical | Major | Normal | Minor
|  | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
1 | <<Sprint number>> | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
2 | Sprint 1 | 0 | 0 | 0 | #REF! | #DIV/0! | PASS | PASS