## Record of Change
Security Classification: Confidential
Document History
Document Location
File Name |  | Location
Assignment2_KimAnh_MiddleTerm.xltx |  | Process Asset Library
Document Version History
Version | Effective Date | Author | Details | Reviewer | Approvers
For previous versions, please refer PIP_Master List

## Instruction
Security Classification: Confidential
| Instruction |  |  |  |  | <<Client Logo>>
| <<Client Name>> |  |  | <<Project Name>>
1. Purpose
Test Case is a set of test inputs, execution conditions, and expected results developed for particular objective, such as to exercise a particular program path or to verify compliance with a specific requirement.
The purpose of the Test Case is to identify and communicate the conditions, which will be implemented and are necessary to verify successful and acceptable implementation of the project.
QC will perform tests and give the result in the test case.
2. How to Use
Test Case List | List all test cases sheet in the file. Each function has a sheet. Generally, each sheet is test case of a UC
Other sheets | There is no specific template for using the test case in the scrum process. It depends on the project, the QC will define how to write test case.
However, how to write test case must be defined in the test strategy/test plan.
There are two samples: "user story 1" and "user story 2"
3. Test Result
Passed | The actual result is met the expected result
Failed | The actual result is NOT met the expected result
Not Run | By some reasons, the cases can't be run: The system has bug and the case can't be run.
4. Bug is not met any case in the test cases
During testing, the QC is able to find a bug which is not met any case in the test case. In this situation, QC need to add the case into the related function as an ad-hoc case.
The step: is the step to reproduce bug.
The expected result: mention the actual and expected result of the bug
Test case #18: Ad-hoc testing
|  | Detail the task as the bug description | Actual result: - - Expectation: - -
5. Test Report
The test report is using for all sprints of the project.

## Cover
Cover
TEST CASE LIST
No. | Sprint # | Function Name | Sheet Name | Description | Pre-Condition
1 |  | Common checklist | Common checklist
2 | Sprint 1 | User Story 1 | User Story 1
3 | Sprint 1 | User Story 2 | User Story 2
4 | Sprint 2
5 | Sprint 2
6 | Sprint 3
7 | Sprint 3

## Common checklist
Common Checklist
No. | Checking item | Expectation | Result
1
2
3
4
5
6
7
8
9
* Note:
[ x ] has verified
Note on D5: Nhan Nguyen Hoang: Yes/No/NA NA: there is no page to check.

## User Story 1
Common Checklist
User Story 1 | Sign in with phone number function | [7 empty] | Pass
Description | [8 empty] | Fail - DE
Pre-condition | Open page log up with phone number
Tested by | Kim Anh
Test Date
Test Result | Internal Build 03112011 | Internal build 14112011 | External build 16112011
Total | 0 | 0 | 0
Passed | 0 | 0 | 0
Failed | 0 | 0 | 0
Not Run | 0 | 0 | 0
NA | 0 | 0 | 0
Passed in previous build | 0 | 0 | 0
Test Result
ID | Test Case Description | Step | Expected Output | Test Data | Internal Build 03112011 | Internal build 14112011 | External build 16112011 | Note
1. Validation field
1.1 Phone number
1 | Verify initial data in phone number field is blank | 1. Observe the search box | Nothing display on search box
2 | Verify sign up but phone number field is empty | 1. Let phone number field empty 2. Click on sign up button | Sign up failed and error message "Please enter Phone number" is displayed
3 | Verify input alphabet and character in phone number field | 1. Click on phone number field 2. Enter abc@# into field 3. Click on sign up button | Sign up failed and error message "Please enter Phone number" is displayed
4 | Verify input space in phone number field | 1. Click on phone number field 2. Enter " " into field 3. Click on sign up button | Sign up failed and error message "Please enter Phone number" is displayed
5 | Verify input HTML, SQL injection in phone number field | 1. Click on phone number field 2. Enter SELECT Phone number FROM users into field 3. Click on sign up button | Sign up failed and error message "Please enter Phone number" is displayed
6 | Verify user can click on button x to clear inputted data | 1. Click on phone number field 2. Enter 0934 into field 3. Click on button x | Data in phone number field is cleared
7 | Verify field let user copy & paste | 1. Click on phone number field 2. Enter 0832017140 3. Copy the phone number above 4. Delete content in phone number field 5. Paste the copied into field 6. Click on sign up button | No error message display in phone number field
8 | Verify total numeric characters input is 10 and valid | 1. Click on phone number field 2. Enter 083201740 into field 3. Click on sign up button | No error message display in phone number field
9 | Verify total numeric characters input is less than 10 and more than 0 | 1. Click on phone number field 2. Enter 09343 into field 3. Click on sign up button | Sign up failed and error message "The length of phone number shoule be 10 characters" is displayed
10 | Verify show error message when total numeric characters input is more than 10 | 1. Click on phone number field 2. Enter 09877769343 into field 3. Click on sign up button | Sign up failed and error message "The length of phone number shoule be 10 characters" is displayed
11 | Verify show error message when phone number input already exists in system | 1. Click on phone number field 2. Enter 083201740 already existed into field 3. Click on sign up button | Sign up failed and error message "Phone number already exists" is displayed
1.2 SMS Verification code
12 | Verify initial data in SMS code field is blank | 1. Observe the SMS Verification field | Nothing display on field
13 | Verify the required SMS code field is empty | 1. Let SMS field empty 2. Click on sign up button | Sign up failed and error message "Please enter SMS Verification code" is displayed
14 | Verify field let user copy & paste | 1. Copy 459883 taken from sms code 2. Click on sms verification field 3. Paste the copied code 4. Click on sign up button | No error message display in phone number field
15 | Verify when input 6 numeric characters do not match with data compared to data from sms phone | 1. Get 459883 in sms phone 2. Click on sms verification field 3. Enter 488g@ 4. Click on sign up button | Sign up failed and error message "Code is wrong " is displayed
16 | Verify input exactly 6 numeric characters match with sms code received from phone | 1. Get 459883 in sms phone 2. Click on sms verification field 3. Enter 459883 4. Click on sign up button | No error message display in phone number field
17 | Verify input exactly 6 numeric characters match with sms code received from phone but it is expired | 1. Get 459883 in sms phone 2. Click on sms verification field after 1 day with same phone number got sms 3. Enter 459883 4. Click on sign up button | Sign up failed and error message "Code is wrong " is displayed
1.3 Password
18 | Verify initial data in password field is blank | 1. Observe the password field | Nothing display on field
19 | Verify input HTML, SQL injection in password field | 1. Click on password field 2. Enter SELECT password FROM users into field 3. Click on sign up button | Sign up failed and error message "Please enter valid password" is displayed
20 | Verify user can click on button x to clear inputted data | 1. Click on password field 2. Enter abc3490 3. Click on button x | Data in password field is cleared
21 | Verify field let user copy & paste | 1. Click on password field 2. Enter abc34 3. Copy the text above 4. Delete content in password field 5. Paste the copied into field 6. Click on sign up button | No error message display in password field
22 | Verify when password contains only alphabetic characters | 1. Click on password field 2. Enter abhdu into field 3. Click on sign up button | Sign up failed and error message "Please enter valid password" is displayed
23 | Verify when password contains only numeric characters | 1. Click on password field 2. Enter 343535 into field 3. Click on sign up button | Sign up failed and error message "Please enter valid password" is displayed
24 | Verify when enter only tab space in password field | 1. Click on password field 2. Enter " " into field 3. Click on sign up button | Sign up failed and error message "Please enter valid password" is displayed
25 | Verify when let password field empty | 1. Let password field empty 2. Click on sign up button | Sign up failed and error message "Please enter password value" is displayed
26 | Verify when total alphabetic and numberic characters in password is less than 6 | 1. Click on password field 2. Enter 3d5 into field 3. Click on sign up button | Sign up failed and error message "Please enter valid password" is displayed
27 | Verify when total alphabetic and numberic characters in password is 6 | 1. Click on password field 2. Enter 349ssd into field 3. Click on sign up button | No error message display in password field
28 | Verify when total alphabetic and numberic characters in password is 50 | 1. Click on password field 2. Enter "123abcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstu" into field 3. Click on sign up button | No error message display in password field
29 | Verify when total alphabetic and numberic characters in password is more than 50 | 1. Click on password field 2. Enter "123abcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyz" into field 3. Click on sign up button | Sign up failed and error message "Please enter valid password" is displayed
30 | Verify when total alphabetic and numberic characters in password is between 6 and 50 | 1. Click on password field 2. Enter 123abc@@ into field 3. Click on sign up button | No error message display in password field
1.4 Birthday
31 | Verify the initial placeholders of birthday field are Month, Day, Year respectively | 1. Observe the password field | Month, Day, Year is placeholder displayed in each box respectively
32 | Verify when enter wrong format of day/month/year in field | 1. Enter 04 in Day field 2. Enter 13 in Month field 3. Enter 20aa in year field 4. Click on sign up button | 1. User can input in field 2.'Sign up failed and error message "Wrong birthday format" is displayed
33 | Verify when enter correct format of day/month/year but day after current day in field | 1. Enter 24 in Day field 2. Enter 10 in Month field 3. Enter 2022 in year field 4. Click on sign up button | Sign up failed and error message "Wrong birthday format" is displayed
34 | Check available values of the Day dropdownlist: - Available values: From 1 to 31 - Sorting: Ascending | 1. Click on Day field dropdown 2. Observe order of day list | 1. User can click on Day dropdown list 2. Day is sorted ascending correctly from 1 to 31
35 | Check available values of the Month dropdownlist - Display value: 1-12 with the name - Sorting: Ascending | 1. Click on Month field dropdown 2. Observe order of month list | 1. User can click on Month dropdown list 2. Month is sorted ascending correctly from 1 to 12 and correct name
36 | Check data in Year field: - Display value: 1900-2022 - Sorting: Descending | 1. Click on Year field dropdown 2. Observe order of year list | 1. User can click on Year dropdown list 2. Year is sorted descending correctly from 1900 to current year(2022) and correct name
37 | Verify available values of Day is changed accordingly when selecting a Month / Year | 1. Click on Year field dropdown 2. Choose year 2020 3. Click on Month field dropdown 4. Choose February in list 3. Click on Day field dropdown 4. Observe day list | It is leap year so there should be changed from 28 day to 29 day options in day dropdown list
38 | Verify birthday field content can be blank | 1. Let birthday field empty 2. Click on sign up button | No error message display in birthday field
1.5 Gender
39 | Verify initial data in gender field is placeholder "Select" | 1. Observe the password field | "Select" is placeholder displayed in box
40 | Verify gender field content can be blank | 1. Let gender field empty 2. Click on sign up button | No error message display in gender field
41 | Verify when input correct format of gender into field | 1. Click on gender field 2. Enter Female 3. Click on sign up button | No error message display in gender field
42 | Verify when input wrong format of gender into field | 1. Click on gender field 2. Enter male23 3. Click on sign up button | 1. Gender field can be edit manually 2. Sign up failed and error message "Wrong gender format" is displayed
43 | Verify gender field can be click on to select option with Male/ Female | 1. Click on gender dropdown 2. Observe data in list | 1. User can click on dropdown 2. Data in list contains Male and Female
1.5 Fullname
44 | Verify initial data in fullname field is blank | 1. Observe the fullname field | Nothing display on field
45 | Verify when enter only tab/spaces in fullname field | 1. Click on fullname field 2. Enter " " 3. Click on sign up button | Sign up failed and error message "Please enter Full Name" is displayed
46 | Verify when fullname field is empty | 1. Let fullname field empty 2. Click on sign up button | Sign up failed and error message "Please enter Full Name" is displayed
47 | Verify automatically trim space from front and end of inputted text | 1. Click on fullname field 2. Enter " John Smith " 3. Click on sign up button | 1. Name created is "John Smith"
48 | Verify user can click on button x to clear inputted data | 1. Click on fullname field 2. Enter "John Smith" 3. Click on button x | Data in fullname field is cleared
49 | Verify show error message when total characters in fullname is less than 6 | 1. Click on fullname field 2. Enter "Mike" 3. Click on sign up button | Sign up failed and error message "The name length should be 6-50 characters" is displayed
50 | Verify show error message when total characters in fullname is more than 50 | 1. Click on fullname field 2. Enter "Mikeabcdefghijklmnopqrstuvwxyzabcdefghijklmn opqrstuv" 3. Click on sign up button | Sign up failed and error message "The name length should be 6-50 characters" is displayed
51 | Verify show error message when total characters in fullname is minlength 6 | 1. Click on fullname field 2. Enter "Mike Jim" 3. Click on sign up button | No error message display in fullname field
52 | Verify show error message when total characters in fullname is maxlength 50 | 1. Click on fullname field 2. Enter "Mikeabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrst" 3. Click on sign up button | No error message display in fullname field
53 | Verify when total characters in fullname field is between 6 and 50 | 1. Click on fullname field 2. Enter "Mike Jackson45" 3. Click on sign up button | No error message display in fullname field
54 | Verify when enter character is not alphabetic or numeric in fullname field | 1. Click on fullname field 2. Enter "Hoang Hai Nam@@#" 3. Click on sign up button | Sign up failed and error message "Wrong format fullname" is displayed
55 | Verify when enter character are alphabetic and numeric in fullname field | 1. Click on fullname field 2. Enter "Hoang Hai Nam" 3. Click on sign up button | No error message display in fullname field
1.6 Checkbox
56 | Verify default value checkbox is checked | 1. Observe the checkbox field | Checkbox is checked
57 | Verfiy checkbox can be click on to uncheck or check | 1. Click on check box to uncheck 2. Click on sign up button | No error happens in checkbox field
1.7 Other
58 | Verify user can click on text link "Term of use" | 1. Click on Term of use | "Term of use" can be clicked on and open the content in a new tab
59 | Verify user can click on text link "Privacy Policy" | 1. Click on Privacy Policy | "Privacy policy" can be clicked on and open the content in a new tab
2. Function
60 | Verify Slide to get SMS code if enter invalid phone number | 1. Click on phone number field 2. Enter 00009993 3. Drag the Slide to get SMS Code | Can not receive any sms code and error message "Please enter a valid phone number" is displayed
61 | Verify Slide to get SMS code if enter valid phone number | 1. Click on phone number field 2. Enter 0979887219 3. Drag Slide to get SMS Code | Slide can be dragged and sms code is sent to following phone number
62 | Verify Slide to get SMS code if do not enter phone number | 1. Let phone number field empty 2. Drag Slide to get SMS Code | Error message "Please enter phone number" is displayed
63 | Verify eye icon can be click to shown/hide password into * in password field | 1. Click on password field 2. Enter abc345@@ as password 3. Click on eye icon | 1. User can click on eye icon 2. Pass will be hide as '*' when click and show off when click again
64 | Verify create account when sign up with mandatory fields only | 1. Enter valid value into only mandatory fields 2. Click on button sign up | 1. No error message is displayed 2. Sign up successly and access to log in account immediately
65 | Verify create account failed when sign up with all invalid fields | 1. Enter invalid value into all fields 2. Click on button sign up | Sign up failed and error message is displayed in each field
66 | Verify button sign up can be clicked on and when all field is validaion | 1. Enter valid value into all fields 2. Click on button sign up | 1. No error message is displayed 2. Sign up successly and access to log in account immediately
67 | Verify sign up with Email | 1. Click on button sign up with Email | 1. Button can be clicked 2. Redirect to Sign up with Email page
68 | Verify sign up with Facebook | 1. Click on button sign up with Facebook | 1. Button can be clicked 2. Redirect to Sign up with Facebook page
69 | Verify sign up with Google | 1. Click on button sign up with Google | 1. Button can be clicked 2. Redirect to Sign up with Google page
Note on F17: Pass Fail Untested N/A
Note on G17: Pass Fail Untested N/A
Note on H17: Pass Fail Untested N/A
Note on F45: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F47: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F48: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F49: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F50: Nguyen Dao Thi Binh: Bug ID: 13057

## Test report
Security Classification: Confidential
|  | End Sprint Test report |  |  |  |  | <<<<Client Logo>>>>
|  | <<<<Client Name>>>> |  |  | <<<<Project Name>>>>
1. Scope of sprint
<<List all the User story which be tested in this sprint, Epic ID and Epic Name field can be removed / modified if needed>>
No. | US ID | US Summary | Epic ID | Epic Name | Environment | Dev Status | QC status | Notes
| <<US ID>> | <<US Summary>> | <<Epic ID>> | <<Epic Name>> | <<Environment>> | <<Dev status>> | <<QC status>>
1 | User Story 1 | US summary | PRT-1 | Epic name 1 | PROD | Done | Done
2 | User Story 2 | US summary 2 | PRT-4 | Epic name 2 | PROD | Done | N/A | Out of scope of testing
2. Test case status in summary
<<List all the test case which be tested for each User story in this sprint>>
No. | US ID | Passed | Failed | N/A | Not Run | Passed in previous builds
| <<US ID>> | <<number of passed>> | <<number of fail cases>> | <<number of n/a>> | <<number of not run>> | <<number of passed in previous build>>
1 | User Story 1 | 0 | 0 | 0 | 0 | 0
2 | Total | 0 | 0 | 0 | 0 | 0
|  | Test coverage | #DIV/0!
3. Bug status
<<The summary information for bugs found in this sprint>>
3.1 Bug summary
No. | Total | New | Resolved | Reopened | Verified / Closed | Note
1 | Critical | #REF! | #REF! | #REF! | #REF!
2 | Major | #REF! | #REF! | #REF! | #REF!
3 | Normal | #REF! | #REF! | #REF! | #REF!
4 | Minor | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | 0 | 0 | #REF!
3.2 Open Bug
No. | Bug ID | Bug Summary | Priority | Environment | Notes
| <<Bug ID>> | <<Bug summary>> | <<Priority>> | <<Environment>>
1 | US3-1 | Bug summary 1 | Minor | PROD
2 | US1-1 | Bug summary | Minor | PROD
4. Risk & Issue
<<Describe the risk, issue, recommendation from QC point of view for this project>>
No. | Description | Mitigation Strategy |  | Contingency (Risk is realized) |  |  | Created Date
1 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
2 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
3 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
5. QC evaluation
<<Describe the QC evaluation for each sprint based on the DoD of project>>
No. | DoD Criteria | Number of Defects |  |  |  | Test coverage | DoD Criteria | QC End Sprint report status
|  | Critical | Major | Normal | Minor
|  | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
1 | <<Sprint number>> | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
2 | Sprint 1 | 0 | 0 | 0 | #REF! | #DIV/0! | PASS | PASS