## Record of Change
Security Classification: Confidential
Document History
Document Location
File Name |  | Location
Assignment2_KimAnh_MiddleTerm.xltx |  | Process Asset Library
Document Version History
Version | Effective Date | Author | Details | Reviewer | Approvers
For previous versions, please refer PIP_Master List

## Instruction
Security Classification: Confidential
| Instruction |  |  |  |  | <<Client Logo>>
| <<Client Name>> |  |  | <<Project Name>>
1. Purpose
Test Case is a set of test inputs, execution conditions, and expected results developed for particular objective, such as to exercise a particular program path or to verify compliance with a specific requirement.
The purpose of the Test Case is to identify and communicate the conditions, which will be implemented and are necessary to verify successful and acceptable implementation of the project.
QC will perform tests and give the result in the test case.
2. How to Use
Test Case List | List all test cases sheet in the file. Each function has a sheet. Generally, each sheet is test case of a UC
Other sheets | There is no specific template for using the test case in the scrum process. It depends on the project, the QC will define how to write test case.
However, how to write test case must be defined in the test strategy/test plan.
There are two samples: "user story 1" and "user story 2"
3. Test Result
Passed | The actual result is met the expected result
Failed | The actual result is NOT met the expected result
Not Run | By some reasons, the cases can't be run: The system has bug and the case can't be run.
4. Bug is not met any case in the test cases
During testing, the QC is able to find a bug which is not met any case in the test case. In this situation, QC need to add the case into the related function as an ad-hoc case.
The step: is the step to reproduce bug.
The expected result: mention the actual and expected result of the bug
Test case #18: Ad-hoc testing
|  | Detail the task as the bug description | Actual result: - - Expectation: - -
5. Test Report
The test report is using for all sprints of the project.

## Cover
Cover
TEST CASE LIST
No. | Sprint # | Function Name | Sheet Name | Description | Pre-Condition
1 |  | Common checklist | Common checklist
2 | Sprint 1 | User Story 1 | User Story 1
3 | Sprint 1 | User Story 2 | User Story 2
4 | Sprint 2
5 | Sprint 2
6 | Sprint 3
7 | Sprint 3

## Common checklist
Common Checklist
No. | Checking item | Expectation | Result
1
2
3
4
5
6
7
8
9
* Note:
[ x ] has verified
Note on D5: Nhan Nguyen Hoang: Yes/No/NA NA: there is no page to check.

## User Story 1
Common Checklist
User Story 1 | Sign in with phone number function | [7 empty] | Pass
Description | [8 empty] | Fail - DE
Pre-condition
Tested by | Kim Anh
Test Date
Test Result | Internal Build 03112011 | Internal build 14112011 | External build 16112011
Total | 0 | 0 | 0
Passed | 0 | 0 | 0
Failed | 0 | 0 | 0
Not Run | 0 | 0 | 0
NA | 0 | 0 | 0
Passed in previous build | 0 | 0 | 0
Test Result
ID | Test Case Description | Step | Expected Output | Test Data | Internal Build 03112011 | Internal build 14112011 | External build 16112011 | Note
1. Validation field
1.1 Phone number
1 | Verify initial data in phone number field is blank
2 | Verify required notice when sign up but phone number field is empty
3 | Verify show error message when input alphabet and character in phone number field
4 | Verify show error message when input space in phone number field
5 | Verify total numeric characters input is 10
6 | Verify total numeric characters input is less than 10 and more than 0
7 | Verify show error message when total numeric characters input is more than 10
8 | Verify show error message when phone number input already exists in system
1.2 SMS Verification code
9 | Verify initial data in SMS code field is blank
10 | Verify show error message when SMS code field is empty
11 | Verify show error message when input alphabet and characters in sms code field
12 | Verify show error message when total numeric characters input is more than 6
13 | Verify show error message when total numeric characters input is more than 0 and less than 6
14 | Verify show error message when input 6 numeric characters but wrong data compared to data from sms phone
15 | Verify input exactly 6 numeric characters sms code received from phone
1.3 Password
16 | Verify initial data in password field is blank
17 | Verify show error message when password contains only alphabetic characters
18 | Verify show error message when password contains only numeric characters
19 | Verify when enter tab space in password field
20 | Verify show error message when let password field empty
21 | Verify show error message when total alphabetic and numberic characters in password is less than 6
22 | Verify show error message when total alphabetic and numberic characters in password is more than 50
23 | Verify when total alphabetic and numberic characters in password is between 6 and 50
1.4 Birthday
24 | Verify initial data in birthday field is blank
25 | Verify show error message when enter wrong format of day/month/year in field
26 | Verify show error message when enter correct format of day/month/year but day after current day in field
27 | Verify birthday field content can be blank
1.5 Gender
28 | Verify initial data in gender field is blank
29 | Verify gender field content can be blank
30 | Verify gender field can be click on to select option
1.5 Fullname
31 | Verify initial data in fullname field is blank
32 | Verify when enter only tab/spaces in fullname field
33 | Verify show error message when let fullname field empty
34 | Verify show error message when total characters in fullname is less than 6
35 | Verify show error message when total characters in fullname is more than 50
36 | Verify when total characters in fullname field is between 6 and 50
37 | Verify input full name with text and more than 50 spaces after text
38 | Verify show error message when enter character is not alphabetic or numeric in fullname field
39 | Verify when enter character are alphabetic and numeric in fullname field
1.6 Checkbox
40 | Verify default value checkbox is checked
41 | Verfiy checkbox can be click on to uncheck or check
2. Function
42 | Verify when phone number is validation, button Slide to get SMS code can be clicked on and new field is displayed
43 | Verify slide sms code field can be hold and slide
44 | Verify sms code is sent to correct phone number in acceptable time
45 | Verify eye icon can be click to shown/hide password into * in password field
46 | Verify show error message when drag sms code slide but phone number is invalid
47 | Verify show error message when drag sms code slide but phone number does not exist
48 | Verify show error message when drag sms code slide but phone number is empty
49 | Verify button sign up can be clicked on and when all field is validation new account is created
50 | Verify user can click on button sign up with Email and go to page sign up with Email
Verify user can click on button sign up with Facebook and a pop up confirmation is displayed
51 | Verify when pop up Facebook show, user can click to confirmed and move to sign up with Facebook page
52 | Verify user can click on button sign up with Google and a pop up confirmation is displayed
53 | Verify when pop up Google show, user can click to select account and move to sign up with Google page
54 | Verify create account failed when click on button sign up but any field is invalid
Note on F17: Pass Fail Untested N/A
Note on G17: Pass Fail Untested N/A
Note on H17: Pass Fail Untested N/A
Note on F31: Nguyen Dao Thi Binh: Bug ID: 13050
Note on F40: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F42: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F43: Nguyen Dao Thi Binh: Bug ID: 13057
Note on F46: Nguyen Dao Thi Binh: Bug ID: 13057

## Test report
Security Classification: Confidential
|  | End Sprint Test report |  |  |  |  | <<<<Client Logo>>>>
|  | <<<<Client Name>>>> |  |  | <<<<Project Name>>>>
1. Scope of sprint
<<List all the User story which be tested in this sprint, Epic ID and Epic Name field can be removed / modified if needed>>
No. | US ID | US Summary | Epic ID | Epic Name | Environment | Dev Status | QC status | Notes
| <<US ID>> | <<US Summary>> | <<Epic ID>> | <<Epic Name>> | <<Environment>> | <<Dev status>> | <<QC status>>
1 | User Story 1 | US summary | PRT-1 | Epic name 1 | PROD | Done | Done
2 | User Story 2 | US summary 2 | PRT-4 | Epic name 2 | PROD | Done | N/A | Out of scope of testing
2. Test case status in summary
<<List all the test case which be tested for each User story in this sprint>>
No. | US ID | Passed | Failed | N/A | Not Run | Passed in previous builds
| <<US ID>> | <<number of passed>> | <<number of fail cases>> | <<number of n/a>> | <<number of not run>> | <<number of passed in previous build>>
1 | User Story 1 | 0 | 0 | 0 | 0 | 0
2 | Total | 0 | 0 | 0 | 0 | 0
|  | Test coverage | #DIV/0!
3. Bug status
<<The summary information for bugs found in this sprint>>
3.1 Bug summary
No. | Total | New | Resolved | Reopened | Verified / Closed | Note
1 | Critical | #REF! | #REF! | #REF! | #REF!
2 | Major | #REF! | #REF! | #REF! | #REF!
3 | Normal | #REF! | #REF! | #REF! | #REF!
4 | Minor | #REF! | #REF! | #REF! | #REF!
| Total | #REF! | 0 | 0 | #REF!
3.2 Open Bug
No. | Bug ID | Bug Summary | Priority | Environment | Notes
| <<Bug ID>> | <<Bug summary>> | <<Priority>> | <<Environment>>
1 | US3-1 | Bug summary 1 | Minor | PROD
2 | US1-1 | Bug summary | Minor | PROD
4. Risk & Issue
<<Describe the risk, issue, recommendation from QC point of view for this project>>
No. | Description | Mitigation Strategy |  | Contingency (Risk is realized) |  |  | Created Date
1 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
2 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
3 | <<Risk which happened in this project>> | <<propose an action to solve this risk>> |  | <<The action needs when the risk is become to issue>>
5. QC evaluation
<<Describe the QC evaluation for each sprint based on the DoD of project>>
No. | DoD Criteria | Number of Defects |  |  |  | Test coverage | DoD Criteria | QC End Sprint report status
|  | Critical | Major | Normal | Minor
|  | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
1 | <<Sprint number>> | <<number of open critical bugs> | <<number of open major bugs>> | <<number of open normal bugs>> | <<number of open minor bugs>> | 100% | PASS | PASS
2 | Sprint 1 | 0 | 0 | 0 | #REF! | #DIV/0! | PASS | PASS